## Timeline
REDfly Timeline |  |  |  | Buffer |  |  |  | 2019
Updated 2019-05-09 |  |  |  | 1 |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Task | Staff | Dur | Type | Weeks | Swk | Ewk | % | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Developmental Staging Data | AVB |  | - |  | 1 | 1 | 0 | May 1: <=; May 2: ==; May 3: ==; May 4: ==; June 5: ==; June 6: ==; June 7: ==; June 8: ==; July 9: ==; July 10: ==; July 11: =>
Batch Upload and Audit | AVB | 4 | s | 4 | 1 | 4 | 50 | bar: May 1 to May 4
Add Staging to Individual Curation | AVB | 4 | s | 4 | 5 | 8 | 25 | bar: June 5 to June 8
User Data Display | AVB | 3 | s | 3 | 9 | 11 | 0 | bar: July 9 to July 11
CRM Segments | AVB |  | - | 0 | 11 | 11 | 0 | July 12: <=; August 13: ==; August 14: ==; August 15: ==; August 16: ==; August 17: ==; September 18: =>
Database Schema Changes | AVB | 1 | s | 1 | 12 | 12 | 0 | bar: July 12
Batch Upload | AVB | 4 | s | 4 | 13 | 16 | 0 | bar: August 13 to August 16
Batch Audit | AVB | 2 | s | 2 | 17 | 18 | 0 | bar: August 17 to September 18
Done! | AVB |  | m | 0 | 18 | 18 | 0 | bar: September 18